## Corporate Site
Sr. No | Owner | Module | Sub-Module | Current Content | Revised / New Content | Comments | Rasied On | KFin Status | Final Nuvama Status
1 | Sonia | Landing Page | - | Investor Grievances: grievance@nuvamamf.in | Investor Grievances: clientservices.mf@nuvama.com |  | 2026-03-27 | Done
2 | Pushkala | Login |  |  | in the privacy policy, the name of the company should be as per the agreement. Sampada to confirm |  | 2026-03-27
3 | Sonia | Landing Page | Nuvama Mutual Fund | Trustworthy investment, shaped by refined ideas from Kirby and Thiel. | Leverages deep research capabilities and disciplined portfolio management to deliver consistent, risk-adjusted returns for its investors. | Landing Page | 2026-03-27 | Done
4 | Sonia | Landing Page | Nuvama Large Cap Fund | A seamless convergence of Nuvama’s proprietary forensic framework with a rules-based approach | An open ended equity scheme predominantly investing in large cap stocks | Landing Page | 2026-03-27 | Done
5 | Pooja | About US | Board of Directors | Photographs missing for NAML Directors | Shared with Raza |  | 2026-03-27 | Done
6 | Pooja | About US | Team | Photo to be updated for Anshu | Shared with Raza | Use the latest Photo of Anshu. In both places (BOD & Team) keep same photo for Anshu | 2026-03-27 | Done
7 | Sonia | About US | Sponsor-Nuvama |  |  | Product Team will check | 2026-03-27
8 | Sonia | Our Funds | Nuvama Large Cap Fund |  | The Scheme aims to provide long-term capital appreciation. It will maintain a minimum exposure of 80% to Large Cap stocks, as defined by SEBI, which currently are the 100 largest companies in India in terms of full market capitalization. Plan available : Direct and Regular Fund Manager: Mr. Ajay Vora (remove date of allotment; please keep others as it is) |  | 2026-03-27 | Done
9 | Sonia | Our Funds | Nuvama Flexi Cap Fund |  | An open ended dynamic equity scheme investing across large cap, mid cap & small cap stocks to generate capital appreciation / income from a portfolio Plan available : Direct and Regular Fund Manager: Mr. Sumit Agrawal (remove date of allotment; please keep others as it is) |  | 2026-03-27 | Done
8 | Sonia | Our Funds | Nuvama Liquid Fund |  | The Fund aims to invest in debt and money market instruments with residual maturity not exceeding 91 days, subject to regulatory changes from time to time. Plan available : Direct and Regular Fund Manager: Mr. Nikhil Ranka (remove date of allotment; please keep others as it is) | 3 schemes added | 2026-03-27 | Done
9 | Pushkala | Knowledge Center | Videos | Place holder kept | Place holder to continue | Investor Grievance Email id to be changed to clientservices.mf@nuvama.com in all pages; please check if the CIN: L67110MH1993PLC344634 SEBI Regn. No. INZ000166136 is correct@ Sampada Mohite to confirm | 2026-03-27
10 | Pushkala | Knowledge Center | Podcast | Place holder kept | Place holder to continue | Investor Grievance Email id to be changed to clientservices.mf@nuvama.com in all pages; please check if the CIN: L67110MH1993PLC344634 SEBI Regn. No. INZ000166136 is correct@ Sampada Mohite to confirm | 2026-03-27
11 | Pushkala | Knowledge Center | Investor Education | Muliple line items mentioned, however no content when clicked on the same. |  | Place holder to be kept for this page and all the line items removed, Investor Grievance Email id to be changed to clientservices.mf@nuvama.com in all pages; please check if the CIN: L67110MH1993PLC344634 SEBI Regn. No. INZ000166136 is correct@ Sampada Mohite to confirm | 2026-03-27
12 | Pushkala | Knowledge Center | Tools & Calculators | Place holder kept | Place holder to continue; Place holder to be kept for this page and all the line items removed, Investor Grievance Email id to be changed to clientservices.mf@nuvama.com in all pages; please check if the CIN: L67110MH1993PLC344634 SEBI Regn. No. INZ000166136 is correct@ Sampada Mohite to confirm |  | 2026-03-27
13 | Pushkala | Knowledge Center | e_KYC | Content on E kyc modes | Current Content is fine; Please check the investor Grievance Email id and check on the CIN and SEBI registeration no |  | 2026-03-27
14 | Pushkala | Knowledge Center | FAQ | FAQs | Current Content is fine; Please check the investor Grievance Email id and check on the CIN and SEBI registeration no |  | 2026-03-27
15 | Pushkala | Downloads | NFO | Place holder kept; content is fine | Place holder to continue; Please check the investor Grievance Email id and check on the CIN and SEBI registeration no .Please refer comments in the earlier module |  | 2026-03-27
16 | Pushkala | Downloads | Investor | Place holder kept; content is fine | Place holder to continue; Please check the investor Grievance Email id and check on the CIN and SEBI registeration no .Please refer comments in the earlier module |  | 2026-03-27
17 | Pushkala | Downloads | Statutory Disclosures | Place holder kept | Place holders to be continued, Grievance email to be changed and CIN and SEBI registration no to be checked |  | 2026-03-27
18 | Pushkala | Downloads | Policies | Place holder kept | Policies are already provided under statutaory disclosures, not required again |  | 2026-03-27
19 | Pushkala | Downloads | Distributor | Place holder kept; content is fine | Place holder kept; content is fine; change the investor grievance email id and check the CIN and SEBI regitration no. |  | 2026-03-27
20 | Pushkala | Downloads | NCT-Forms | Place holder kept; content is fine | Place holder kept; content is fine; change the investor grievance email id and check the CIN and SEBI regitration no. |  | 2026-03-27
21 | Sonia | Investor Center | MF Scheme List | Nuvama Large Cap Fund | The Scheme aims to provide long-term capital appreciation. It will maintain a minimum exposure of 80% to Large Cap stocks, as defined by SEBI, which currently are the 100 largest companies in India in terms of full market capitalization. Plan available : Direct and Regular |  | 2026-03-27 | Done
| Sonia | Investor Center |  | Nuvama Flexi Cap Fund | An open ended dynamic equity scheme investing across large cap, mid cap & small cap stocks to generate capital appreciation / income from a portfolio Plan available : Direct and Regular |  | 2026-03-27 | Done
| Sonia | Investor Center |  | Nuvama Liquid Fund | The Fund aims to invest in debt and money market instruments with residual maturity not exceeding 91 days, subject to regulatory changes from time to time. Plan available : Direct and Regular |  | 2026-03-27 | Done
22 | Pushkala | Investor Center | RTA Branch Details |  | Details are fine |  | 2026-03-27
23 | Pushkala | Investor Center | Feedback Form |  | Details are fine |  | 2026-03-27
24 | Pushkala | Investor Center | Queries and Complaints |  | - Change Pushkala Roy Choudhury ( IRO ) no to +91 90764 40280, - Change level 3 to Call or write to our CEO should be Call or write to our COO, mobile no: +91 93222 50957, - In the part of remedy through Regulator viz SEBI, change the name of the mutual fund to Nuvama Mutual instead of Capital Mind Mutual Fund; - Remove Toll Free no: 18005693031 from SEBI Toll free no. - In Smart ODR section, replace Capital Mind MF name with Nuvama Mutual Fund - Change the grievance Email id to clientservices.mf@nuvama.com and check the CIN and SEBI registration no and input the correct no. |  | 2026-03-27 | Done
25 | Pushkala | Contact | Contact |  |  | Pushkala to check and confirm

## Old Corporate Site (hidden)
Sr. No | Owner | Module | Sub-Module | Current Content | Revised / New Content | Comments | Rasied On | KFin Status | Final Nuvama Status
1 | Sonia | Landing Page | - | Investor Grievances: grievance@nuvamamf.in | Investor Grievances: clientservices.mf@nuvama.com |  | 27th March 2026
2 | Pushkala | Login |  |  | Place holder kept; content is fine; change the investor grievance email id and check the CIN and SEBI regitration no. |  | 27th March 2026
3 | Sonia | About US | Nuvama Mutual Fund | Trustworthy investment, shaped by refined ideas from Kirby and Thiel. | Leverages deep research capabilities and disciplined portfolio management to deliver consistent, risk-adjusted returns for its investors. | Landing Page | 27th March 2026
4 | Pooja | About US | Nuvama Large Cap Fund | A seamless convergence of Nuvama’s proprietary forensic framework with a rules-based approach | An open ended equity scheme predominantly investing in large cap stocks | Landing Page | 27th March 2026
5 | Pooja | About US | Board of Directors | Photographs missing for NAML Directors | Shared with Raza |  | 27th March 2026
6 | Pooja | About US | Team | Photo to be updated for Anshu | Shared with Raza |  | 27th March 2026
7 | Sonia | About US | Sponsor-Nuvama |  |  | Unclear
8 | Sonia | Our Funds | Nuvama Large Cap Fund |  | The Scheme aims to provide long-term capital appreciation. It will maintain a minimum exposure of 80% to Large Cap stocks, as defined by SEBI, which currently are the 100 largest companies in India in terms of full market capitalization. Plan available : Direct and Regular Fund Manager: Mr. Ajay Vora (remove date of allotment; please keep others as it is) |  | 27th March 2026
9 | Sonia | Our Funds | Nuvama Flexi Cap Fund |  | An open ended dynamic equity scheme investing across large cap, mid cap & small cap stocks to generate capital appreciation / income from a portfolio Plan available : Direct and Regular Fund Manager: Mr. Sumit Agrawal (remove date of allotment; please keep others as it is) |  | 27th March 2026
8 | Sonia | Our Funds | Nuvama Liquid Fund |  | The Fund aims to invest in debt and money market instruments with residual maturity not exceeding 91 days, subject to regulatory changes from time to time. Plan available : Direct and Regular Fund Manager: Mr. Nikhil Ranka (remove date of allotment; please keep others as it is) | 3 schemes added | 27th March 2026
9 | Pushkala | Knowledge Center | Videos | Place holder kept | Place holder to continue | Investor Grievance Email id to be changed to clientservices.mf@nuvama.com in all pages; please check if the CIN: L67110MH1993PLC344634 SEBI Regn. No. INZ000166136 is correct@ Sampada Mohite to confirm | 27th March 2026
10 | Pushkala | Knowledge Center | Podcast | Place holder kept | Place holder to continue | Investor Grievance Email id to be changed to clientservices.mf@nuvama.com in all pages; please check if the CIN: L67110MH1993PLC344634 SEBI Regn. No. INZ000166136 is correct@ Sampada Mohite to confirm | 27th March 2026
11 | Pushkala | Knowledge Center | Investor Education | Muliple line items mentioned, however no content when clicked on the same. |  | Raza to speak to MS, if required, we can remove click here button. | 27th March 2026
12 | Pushkala | Knowledge Center | Tools & Calculators | Place holder kept | Place holder to continue; Place holder to be kept for this page and all the line items removed, Investor Grievance Email id to be changed to clientservices.mf@nuvama.com in all pages; please check if the CIN: L67110MH1993PLC344634 SEBI Regn. No. INZ000166136 is correct@ Sampada Mohite to confirm |  | 27th March 2026
13 | Pushkala | Knowledge Center | e_KYC | Content on E kyc modes | Current Content is fine; Please check the investor Grievance Email id and check on the CIN and SEBI registeration no |  | 27th March 2026
14 | Pushkala | Knowledge Center | FAQ | FAQs | Current Content is fine; Please check the investor Grievance Email id and check on the CIN and SEBI registeration no |  | 27th March 2026
15 | Pushkala | Downloads | NFO | Place holder kept; content is fine | Place holder to continue; Please check the investor Grievance Email id and check on the CIN and SEBI registeration no .Please refer comments in the earlier module |  | 27th March 2026
16 | Pushkala | Downloads | Investor | Place holder kept; content is fine | Place holder to continue; Please check the investor Grievance Email id and check on the CIN and SEBI registeration no .Please refer comments in the earlier module |  | 27th March 2026
17 | Pushkala | Downloads | Statutory Disclosures | Place holder kept | Place holders to be continued, Grievance email to be changed and CIN and SEBI registration no to be checked |  | 27th March 2026
18 | Pushkala | Downloads | Policies | Place holder kept | Policies are already provided under statutaory disclosures, not required again |  | 27th March 2026
19 | Pushkala | Downloads | Distributor | Place holder kept; content is fine | Place holder kept; content is fine; change the investor grievance email id and check the CIN and SEBI regitration no. |  | 27th March 2026
20 | Pushkala | Downloads | NCT-Forms | Place holder kept; content is fine | Place holder kept; content is fine; change the investor grievance email id and check the CIN and SEBI regitration no. |  | 27th March 2026
21 | Pushkala | Investor Center | MF Scheme List | Please check with Product team |  |  | 27th March 2026
22 | Pushkala |  | RTA Branch Details |  | Details are fine |  | 27th March 2026
23 | Pushkala |  | Feedback Form |  | Details are fine |  | 27th March 2026
24 | Pushkala | Contact | Queries and Complaints |  | Change Pushkala roy Choudhury ( IRO ) no to +91 90764 40280, Change level 3 to Call or write to our COO, mobile no: 9322250957, In the part of remedy through Regulator viz SEBI, change the name of the mutual fund to Nuvama Mutual instead of Capital Mind Mutual Fund; Remove Toll Free no: 18005693031 from SEBI Toll free no. In Smart ODR section, replace Capital Mind MF name with Nuvama Mutual Fund; Change the grievance Email id and check the CIN and SEBI registration no and input the correct no. |  | 27th March 2026
25 |  |  | Contact

## Investor Site
Sr. No | Module | Sub-Module | Current Content | Revised / New Content | Comments | Raised By | Rasied On | KFin Status | Final Nuvama Status

## DIT
Sr. No | Module | Sub-Module | Current Content | Revised / New Content | Comments | Raised By | Rasied On | KFin Status | Final Nuvama Status

## Distributor empanelment Maker
Sr. No | Module | Sub-Module | Current Content | Revised / New Content | Comments | Raised By | Rasied On | KFin Status | Final Nuvama Status

## Distributor empanelment Checker
Sr. No | Module | Sub-Module | Current Content | Revised / New Content | Comments | Raised By | Rasied On | KFin Status | Final Nuvama Status